## budget
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| IQS | HSJD | 5RF | RDB | UAO | ESADE | BBU | FCRI | NTNU | TUM | WEDO | UG | TOTAL | %
WP1 |  | 6 |  |  | 12 |  | 3 |  | 5 |  |  | 6 | 32 | 4.219%
WP2 | 11 |  |  |  | 13 |  | 7 |  | 34 | 4 |  | 6 | 75 | 9.888%
WP3 | 6 | 33 |  |  | 23 |  | 32 | 18 |  |  |  |  | 112 | 14.77%
WP4 | 15 |  |  | 26 |  | 15 | 10 | 28 |  | 5 | 2 |  | 101 | 13.32%
WP5 | 30 |  | 3 |  |  | 36 | 22 |  |  | 10 | 2 |  | 103 | 13.58%
WP6 | 38 |  | 18 |  |  |  | 13 | 17 | 14 | 5 |  |  | 95 | 12.52%
WP7 | 13 |  | 5 |  | 7.5 |  | 6.5 | [5 empty] | 32 | 4.219%
WP8 | 3.5 |  | 20 |  |  | 3 | 0 | 9 |  |  |  |  | 35.5 | 4.68%
WP9 | 12 | 3 | 6 | 3 | 3 | 3 | 3 | 6 | 3 | 3 | 50 | 3 | 98 | 12.92%
WP10 | 30 | 6 |  |  | 6 | 6 |  | 6 | 6 |  | 15 |  | 75 | 9.888%
| 158.5 | 48 | 52 | 29 | 64.5 | 63 | 96.5 | 84 | 62 | 27 | 69 | 15 | 758.5 | 100%
0%
Average personnel rate | 6200 | 5500 | 8000 | 6000 | 5500 | 6200 | 4500 | 5500 | 8000 | 6000 | 5500 | 8000
Overhead rate | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
% EU contribution | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
RTD or INNOVATION ? | RTD | RTD | RTD | RTD | RTD | RTD | RTD | RTD | RTD | RTD | RTD | RTD
BUDGET
EFFORT | 158.5 | 48 | 52 | 29 | 64.5 | 63 | 96.5 | 84 | 62 | 27 | 69 | 15 | 768.5 | %
PERSONNEL | 982700 | 264000 | 416000 | 174000 | 354750 | 390600 | 434250 | 462000 | 496000 | 162000 | 379500 | 120000 | 4635800 | 60.11%
Travel & Meetings (including dissemination) | 22500 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 187500
Travel SAB | 10000 | [11 empty] | 10000
Attendance to regular joint meetings & other potential joint activities | [12 empty] | 0
Communication tools | [10 empty] | 80000 |  | 80000
Publications in open access | 12000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 3000 | 6000 | 75000
Expenses for workshops, intervention meetings, webinars, trainings |  |  | 75000 |  |  |  |  | 75000 |  | 25000 |  |  | 175000
Consumables, licenses and software | 100000 | 80000 |  | 150000 | 100000 | 100000 | 100000 | 75000 | 50000 |  |  | 100000 | 855000
Insurances |  | 20000 | [10 empty] | 20000
Equipment | [12 empty] | 0
Final Conference | 40000 | [9 empty] | 25000 |  | 65000
Audit certificates (only partners surpassing 430,000 funding) | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 |  | 6000 | 6000 | 66000
Other direct costs | [12 empty] | 0
TOTAL OTHER DIRECT COSTS | 190500 | 127000 | 102000 | 177000 | 127000 | 127000 | 127000 | 177000 | 77000 | 46000 | 129000 | 127000 | 1533500 | 19.89%
SUBCONTRACTING | [12 empty] | 0
OVERHEADS | 293300 | 97750 | 129500 | 87750 | 120437.5 | 129400 | 140312.5 | 159750 | 143250 | 52000 | 127125 | 61750 | 1542325 | 20%
TOTAL COSTS | 1466500 | 488750 | 647500 | 438750 | 602187.5 | 647000 | 701562.5 | 798750 | 716250 | 260000 | 635625 | 308750 | 7711625 |  | LIMIT TO FUNDING
EC FUNDING | 1466500 | 488750 | 647500 | 438750 | 602187.5 | 647000 | 701562.5 | 798750 | 716250 | 260000 | 635625 | 308750 | 7711625 |  | 288375
% | 19.02% | 6.338% | 8.396% | 5.689% | 7.809% | 8.39% | 9.097% | 10.36% | 9.288% | 3.372% | 8.242% | 4.004%
Audit certificate? | YES | YES | YES | YES | YES | YES | YES | YES | YES |  | YES
FTE | 2.6417 | 0.8 | 0.86667 | 0.48333 | 1.075 | 1.05 | 1.6083 | 1.4 | 1.0333 | 0.45 | 1.15 | 0.25 | 12.8083
Other costs surpassing 15% of personnel | 19.39% | 48.11% | 24.52% | 101.7% | 35.8% | 32.51% | 29.25% | 38.31% | 15.52% | 28.4% | 33.99% | 105.8%

## gantt
| M2 | M4 | M6 | M8 | M10 | M12 | M14 | M16 | M18 | M20 | M22 | M24 | M26 | M28 | M30 | M32 | M34 | M36 | M38 | M40 | M42 | M44 | M46 | M48 | M50 | M52 | M54 | M56 | M58 | M60
WP1. Conceptual framework, DDRI and cross-context measurement backbone design | bar: M2 to M12
T1.1 State-of-the-art synthesis and developmental benchmarking | bar: M2 to M4
T1.2 Framework specification and DDRI architecture design | bar: M4 to M6
T1.3 Cross-WP measurement backbone design | bar: M6 to M8
T1.4 Feasibility, burden, and implementation-ready measurement package | bar: M8 to M12
WP2. Data integration, harmonisation and FAIR evidence backbone
T2.1 Data governance, access framework and project-wide DMP implementation | bar: M2 to M60
T2.2 Metadata architecture, variable dictionaries and harmonisation rules | bar: M4 to M12
T2.3 Cohort-data extraction, curation, cross-cohort harmonisation and cohort-linked enrichment sub-studies | bar: M6 to M30
T2.4 Metadata architecture, variable dictionaries and harmonisation rules | bar: M10 to M60
WP3. Early-warning markers of digital vulnerability in sensitive developmental windows | bar: M14 to M48
T3.1 Study setup and implementation across study sites | bar: M14 to M18
T3.2 Baseline profiling of regulatory vulnerability and digital-use patterns | bar: M16 to M30
T3.3 Repeated ecological assessment of digital coping, affective dynamics, and nighttime use | bar: M18 to M36
T3.4 Neurocognitive assessment across sensitive developmental windows | bar: M18 to M36
T3.5 Focused exploratory neurofunctional sub-study and early-warning marker derivation | bar: M22 to M48
WP4. School-based digital self-regulation, resilience and gaming literacy intervention | bar: M14 to M48
T4.1 Co-design, intervention framework and school protocol finalisation | bar: M14 to M18
T4.2 Intervention development, bounded gameplay component, and pilot refinement | bar: M20 to M30
T4.3 Cluster-randomised school implementation in Catalonia and a complementary Romanian site | bar: M26 to M36
T4.4 Cognitive/behavioural, mixed-methods and exploratory moderator analysis | bar: M30 to M42
T4.5 Transfer to validation, school uptake and family-facing prevention resources | bar: M42 to M48
WP5. AI use, loneliness and bounded support in young-adult transitions | bar: M14 to M48
T5.1 Conceptual framework, protocol and harmonised measures | bar: M14 to M18
T5.2 Co-design of bounded AI-use conditions and safeguards | bar: M20 to M24
T5.3 Multi-site experimental study on AI use conditions in young adults | bar: M26 to M36
T5.4 Mixed-methods follow-up on real-world AI reliance, loneliness and support substitution | bar: M30 to M42
T5.5 Mechanism, moderator and simulation-parameter analysis | bar: M42 to M48
WP6. School digital governance comparison and simulation | bar: M14 to M48
T6.1 Governance framework and comparative mapping across school contexts | bar: M14 to M18
T6.2 Comparative analysis of governance configurations and natural experiments | bar: M20 to M24
T6.3 ABM scenario engine design and parameterisation using WP1–WP5 evidence | bar: M26 to M36
T6.4 Simulation of alternative school digital governance scenarios | bar: M30 to M42
T6.5 Transfer, interpretation and policy translation of model outputs | bar: M42 to M48
WP7. Multidimensional structuring and operationalization of the DDR index | bar: M36 to M60
T7.1 Cross-WP integration architecture, evidence matrix and structured comparison framework | bar: M36 to M42
T7.2 Multidimensional structuring of the DDRI across settings | bar: M40 to M48
T7.3 Cross-WP interpretive integration, transferability assessment and empirical–simulated comparison | bar: M48 to M54
T7.4 Integrated evidence package for downstream translation | bar: M56 to M60
WP8. Scale-up and policy recommendations | bar: M36 to M60
T8.1 Cross-WP evidence consolidation and translational framework | bar: M36 to M44
T8.2 Development of recommendation packages across governance, prevention and bounded AI-use domains | bar: M44 to M54
T8.3 Scale-up readiness, uptake packaging and final transfer framework | bar: M54 to M60
WP9. Impact Maximization
T9.1 Plan for Dissemination, Communication and Exploitation | bar: M2 to M60
T9.2 MILESTONES dissemination and communication tools and activities communications | bar: M2 to M60
T9.3 MILESTONES engagement
T9.4 KERs Exploitation and Legacy
T9.5 Cluster Interface and Collaboration
WP10. Project Management and Coordination
T10.1 Establish and implement the project management structure | bar: M2 to M60
T10.2 Day-to-day project management
T10.3 Ethical, legal and social implications management
T10.4 Quality management, risk management and conflict resolution

## INPUTS (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| UH | WeDo | BIU | JU | RegionH | NUR | AE | EHMA | OHE | UA | BFH | CHUV | IAPO | CSFJA | SAS
PERSONNEL
Person-months | 205.2 |  | 97.2 | 70.2 | 89.1 |  |  | 29.7 | 11.34 | 34.7 | 78.3 | 37.8 | 59.4 | 21.6 | 32.4
Personnel costs (€) | 4753.1579 | 5500 | 3164.6841 | 2376.5 | 9792.7 |  |  | 2020 | 10615.07 | 6930 | 15810 | 7470 | 5387.5 | 4000 | 4500
Total Personnel costs (€) | 975348 | 0 | 307607.2934 | 166830.3 | 872529.57 | 0 | 0 | 59994 | 120374.8938 | 240471 | 1237923 | 282366 | 320017.5 | 86400 | 145800
TRAVEL
| 8100 | [8 empty] | 6000
| 17200 | [8 empty] | 1000
EQUIPMENT
| 8000 |  |  | 4500 | 20000 | [9 empty] | 1000
OTHER COSTS
Site | 100000
Helsinki | 3000
Cost of Financial Certificates | 6750
workshop in HU | 15000
Publications in open access | 25000 |  |  | 10000 | [5 empty] | 1500
Translation | [13 empty] | 10000 | 10000
Consumables |  |  |  | 5000
Other goods/ Services |  |  | 3000 | [6 empty] | 1700
SUBCONTRACTORS | [9 empty] | 51000 |  |  |  | 24300 | 50000
20000
INDIRECT COSTS | 8000 |  | 77652
TOTAL | 1166398 | 0 | 388259.2934 | 206330.3 | 892529.57 | 0 | 0 | 59994 | 120374.8938 | 301671 | 1237923 | 282366 | 320017.5 | 120700 | 206800
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| UH | WeDo | BIU | JU | RegionH | NUR | AE | EHMA | OHE | UA | BFH | CHUV | IAPO | CSFJA | SAS
| 4753 | 5500 | 3165 | 2380 | 9793 | 6700 | 6800 | 2020 | 10615 | 6930 | 15810 | 7470 | 5437.5 | 4000 | 4500
BUDGET
EFFORT | 123.6 | 47.9 | 31.7 | 66.4 | 49.2 | 47.6 | 12.1 | 15 | 8.4 | 46.5 | 25.9 | 59.3 | 14.2 | 1.4 | 50.9
PERSONNEL | 587471 | 263450 | 100331 | 158032 | 481816 | 318920 | 82280 | 30300 | 89166 | 322245 | 409479 | 442971 | 77213 | 5950 | 203600
Travel & Meetings (including dissemination) | 25000 | 11600 | 9000 | 9200 | 10100 | 7200 | 8100 | 6400 | 8100 | 9600 | 8900 | 7600 | 7200 | 10000 | 8000
Travel SAB | 20800
Attendance to regular joint meetings & other potential joint activities | 18000 | 10000 |  | 3000 | 3000 | 3000 | 5000 | 5000 | 4000 |  | 3000 | 3000
Communication tools |  | 40000
Publications in open access | 25000 |  | 3500 | 3500 | 3500 | 3500 |  |  | 6000 | 1500 |  | 3500
Expenses for workshops and AFeCTS-SF meetings |  | 5000 |  |  |  |  | 51000 | 15000 |  |  |  |  | 15000
Consumables, licenses and software |  |  |  |  | 16500 | 1566
Translations (surveys, platform, intervention material)
Site monitoring travel | [9 empty] | 1000
Equipment | 8000 |  |  | 4500
Final Conference |  | 59725
Audit certificates (only partners surpassing 425,000 funding) | 6750 | 4000 |  |  | 4000
Other direct costs | 50000 |  | 3000 | 10000 | [5 empty] | 1700
TOTAL OTHER DIRECT COSTS | 128800 | 130325 | 15500 | 30200 | 37100 | 15266 | 64100 | 26400 | 18100 | 13800 | 11900 | 14100 | 22200 | 10000 | 8000
SUBCONTRACTING | 75000 |  |  | 20000 | [5 empty] | 51000
OVERHEADS | 179067.75 | 98443.75 | 28957.75 | 47058 | 129729 | 83546.5 | 36595 | 14175 | 26816.5 | 84011.25 | 105344.75 | 114267.75 | 24853.25 | 19937.5 | 52900
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PI's will travel abroad once a year
Note on L11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tarvel costs (2x per year) to partner countries
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 Advisory bord meeting in Israel
Note on L12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Relation-oriented costs
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 computers
Note on Q14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Laptop
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Publications & Editing
Note on L20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Editing paper scientifique journal
Note on L23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Printing + statistics
Note on E39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated by BIU 97,20
Note on C43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: workshop in HU + Helsinki
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Laboratory analyses
Note on H47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.500 EUR for survey license
Note on F50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Laptops
Note on L53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Printing + statistics
Note on C55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Setting: Maccabi Health care services (HMO)
Note on F55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intervention site
Note on L55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intervention sites Reply: 17000€/YEAR = 51.000€

## TRAVEL (hidden)
| TRAVEL COSTS |  | ES | ES | NL | UK | ES | IT | IT | ES | ES | FR | FR | IT
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 11 | 12 | 13 |  |  | 15
|  |  | GENCAT | SIRIS | UTRECHT | SPRU | WEDO | RER | ARTER | FUB | EURECAT | UPEC | GPSEA | UNIBO |  |  | #REF!
|  | HOST | T.Fernández | F.Massucci | C.Alvial | M.Ramirez | A.Honrado | A.Daraio | G.Moretti | X.Gironés | R.Elelman | P.Savidan | S. Despots | M. Fia | Attendes |  | SAB· | AT
M1 | Kick-off meeting | GENCAT (Barcelona) | 4 | 3 | 3 | 2 | 3 | 3 | 3 | 4 | 2 | 3 | 1 | 1 | 37 |  | 5
M5 | C. Meeting + Local workshops | GPSEA (Crèteil) | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 25
M21 | Local workshops | GPSEA (Crèteil) | ES 2: 2; NL 3: 2; UK 4: 2; ES 5: 2; FR 11: 2; FR 12: 1 | 11
M22 | Local workshops | ART-ER (Emilia Romagna) | ES 2: 2; NL 3: 2; UK 4: 2; ES 5: 2; IT 6: 3; IT 7: 3; IT 13: 1 | 16 |  | 1
M25 | Local workshops | FUB (Manresa) | ES 1: 2; ES 2: 2; NL 3: 2; UK 4: 2; ES 5: 3; ES 8: 2; ES 9: 2 | 15
M34 | I. Conference + C. Meeting | WEDO (Brussels) | 4 | 3 | 3 | 2 | 3 | 3 | 3 | 4 | 2 | 3 | 1 | 1 | 39 |  | 5 | 2
M36 | Closing meeting | GENCAT (Barcelona) | 4 | 3 | 3 | 2 | 3 | 3 | 3 | 4 | 2 | 3 | 1 | 1 | 32
|  | Nº Travels | 6 | 9 | 17 | 14 | 10 | 9 | 15 | 16 | 4 | 7 | 5 | 5
|  | TOTAL TRAVEL | 5200 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  | 9300 | 21000 | 30300
Destinations
| Spain | 800 | NL 3: Host / No travel
| Italy | 800 | NL 3: No host /No travel
| Netherlands | 900 | NL 3: Host / Travel
| United Kingdom | 900
| France | 800
| Belgium | 900
| Australia | 4000
| Colombia | 3000
ORGANISATION COSTS
|  |  | ES 2: Public meetings and conferences; IT 6: Consortium meetings and partners workshops | Wedo
[12 empty] | Total amount | Total attendees
|  | HOST | Location | Attendees | VENUE | CATERING | TOTAL | Attendees | VENUE | CATERING | TOTAL |  |  |  | Material for workshops | AVT and Other Logistic | Travel for SAB and guest attendees/speakers
M1 | Kick-off meeting | WEDO (Barcelona) | Barcelona | 100 | 0 | 6000 | 6000 | 37 | 0 | 2220 | 2220 | 8220 | 137
M5 | C. Meeting + Local workshops | GPSEA (Crèteil) | Crèteil | 25 | 0 | 1125 | 1125 | 25 | 0 | 1125 | 1125 | 2250 | 50
M10 | C. Meeting + Local workshops | ART-ER (Emilia Romagna) | R Emilia R | 50 | 0 | 2250 | 2250 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M13 | Local workshops | ART-ER (Emilia Romagna) | R Emilia R | 50 | 0 | 1500 | 1500 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M15 | C. Meeting + Local workshops | FUB (Manresa) | Manresa | 50 | 0 | 2250 | 2250 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M16 | Local workshops | GPSEA (Crèteil) | Crèteil | 20 | 0 | 600 | 600 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M18 | Local workshops | ART-ER (Emilia Romagna) | R Emilia R | 20 | 0 | 600 | 600 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M19 | Local workshops | FUB (Manresa) | Manresa | 20 | 0 | 600 | 600 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M21 | Local workshops | GPSEA (Crèteil) | Crèteil | 20 | 0 | 600 | 600 | 11 | 0 | 330 | 330 | 930 | 31
M22 | Local workshops | ART-ER (Emilia Romagna) | R Emilia R | 20 | 0 | 600 | 600 | 16 | 0 | 480 | 480 | 1080 | 36
M25 | Local workshops | FUB (Manresa) | Manresa | 20 | 0 | 600 | 600 | 15 | 0 | 450 | 450 | 1050 | 35
M26 | C. Meeting + Local workshops | GPSEA (Crèteil) | Crèteil | 20 | 0 | 600 | 600 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M30 | P. Meeting + Local workshops | ART-ER (Emilia Romagna) | R Emilia R | 50 | 0 | 2250 | 2250 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M33 | P. Meeting | GPSEA (Crèteil) | Crèteil | 50 | 0 | 2250 | 2250 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M34 | P. Meeting | FUB (Manresa) | Manresa | 50 | 0 | 1500 | 1500 | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
M34 | I. Conference + C. Meeting | WEDO (Brussels) | Brussels | 100 | 0 | 2000 | 2000 | 39 | 0 | 0 | 0 | 2000 | 139
M36 | Closing meeting | WEDO (Barcelona) | Barcelona | 150 | 0 | 4500 | 4500 | 32 | 0 | 1600 | 1600 | 6100 | 182 |  | 1820 | 2000 | 10400
#REF!
| GENCAT |  | ES 2: Catering / cost
| GPSA | #REF! | ES 2: High; UK 4: 60
| FUB | #REF! | ES 2: Medium; UK 4: 45
| ART-ER | #REF! | ES 2: Low; UK 4: 30
| WEDO | 30540 | ES 2: Breakfast; UK 4: 20
|  | #REF! | ES 2: Pre-Conference dinner; UK 4: 50
| Total Meetings | 17
| Total Amount | #REF!
| Meeting average | #REF!
Note on R5: SAB: · 5 total people · 3 meetings · All Europe-based
Note on S5: ATs · 2 ATs: Australia & Colombia · 3 meetings
Note on G47: breakfast, finger lunch and coffee
Note on R47: 3 SAB + 10 special attendees