RECOMMENDATIONS WHEN DRAFTING A WORK PACKAGE DESCRIPTION

Work packages and tasks

- Work packages should have a length of 2 to 4 pages. They are operative execution descriptions with specific activities and results. Bear in mind that descriptions in detail and project design aspects are introduced in previous sections of the proposal, so try to avoid including rationales or technical backgrounds.

- Work Packages should be easy-to-understand, giving a clear picture of the different tasks, inputs, outputs, timings, and actors involved (who is leading the task and who is participating), as well as the technical sequence and the different connections between activities both within the work package and with other work packages.

- Given the page limit, avoid the inclusion of pictures and graphs unless they give meaningful information.

Objectives

- Objectives should be straightforward and listed using bullet points. Five to six objectives should be enough in order to help reviewers to clearly identify the outcomes and purposes of the tasks within each work package.

Deliverables

- Deliverables results produced in the course of the technical execution. They allow project-tracking and can be of different nature: reports (interim and final), publicatinos, protocols, prototypes, software, etc.

- Try to identify the right amount of deliverables. They should allow the commission tracking the execution of a work package throughout its life. Avoid an overload of deliverables all at the same time or with same responsible partner. Remember: more does not always mean better.

- All deliverables should have a small description (1-2 lines) that help reviewers to understand their nature and content.

- Number de deliverables with a D + the work package number + the deliverable number (assigned from the earliest one to the last one according to due date)

Example of deliverable format and content: D1.1 Project handbook (Month 4). This deliverable is intended to serve as a quick reference ‘manual’ for partners to consult management procedures. It will summarise the key provisions in the Consortium Agreement and the Grant Agreement in lay terms and explain the organisational structure, internal policies and procedures.

Milestones

- They are significant moments in the project life where decisions are made regarding the right accomplishment of the project objectives and/or the continuity of the project activities.

- You should be able to identify the WPs involved, the due date, and the means to verify the attainment of the milestone. Deliverables are a possible mean of verification that milestones are accomplished.

- Try to phrase milestones in terms of actions such as: Finalisation of, Publication of, Successful completion of, Submission of, Presentation of, Conclusion of, Attendance to, Organization of, Implementation of, etc.

- If you have more than one milestone defined, compare them and try to assess if they are all key for the project continuity or if they all contain a go-no go decision. If so, try to prioritize them and keep the ones that are on top of the list.

Example of milestones.

| Mil # | Milestone name | WPs involved | Due date | Means of verification |
| --- | --- | --- | --- | --- |
| Mx | Completion of prospective evaluation activities | WP6 | Month 32 | D6.5 and D6.6 submitted |

Table 3.1a. Work packages description.

| Work package number | WPX |  | Start Date |  |  | Month 1 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 |  | 3 | 4 |  | 5 | 6 |
| Short name of participant |  |  |  |  |  |  |  |  |
| Person-months per participant | - | - |  | - | - |  | - | - |

| Objectives ... … … … |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description of work |  |  |  |  |  |
| Task X.1 Task Name (from Month X to Month Y) |  |  |  |  |  |
| Partners involved |  |  |  | Task leader and participants |  |
| Task X.2 Task Name (from Month X to Month Y) |  |  |  |  |  |
| Partners involved |  | Task leader and participants |  |  |  |
| - Task X.3 Task Name (from Month X to Month Y) |  |  |  |  |  |
| - Partners involved |  |  | - Task leader and participants |  |  |
| Task X.4 Task Name (from Month X to Month Y) |  |  |  |  |  |
| Partners involved |  |  | Task leader and participants |  |  |
| - Task X.5 Task Name (from Month X to Month Y) |  |  |  |  |  |
| - Partners involved | - Task leader and participants |  |  |  |  |
| Deliverables DX.1 Deliverable name (MX) - Deliverable description DX.2 Deliverable name (MX) - Deliverable description D1.3 Deliverable name (MXX) - Deliverable description |  |  |  |  |  |

Table 3.2a. List of milestones.

| Milestone number | Milestone name | Related work package(s) | Estimated date | Means of verification |
| --- | --- | --- | --- | --- |
| MX.1 |  | WPX | MX |  |
| MX.2 |  | WPX | MX |  |